## Sheet1
Sprint # | Sprint Dates | Major Goals | Tasks / Deliverables | Assigned To | Status | % Complete | Notes
Sprint 1 | Oct 7 – Oct 20 | Requirements & Setup | Define SRS, set up repo, plan tasks | All | Complete | 100% | Submitted to instructor
Sprint 2 | Oct 21 – Nov 3 | Core CRUD | Build product add/edit/delete, database connection |  | In Progress | 70% | Test database updates
Sprint 3 | Nov 4 – Nov 17 | Barcode & Inventory History | Integrate scanner input, item history tracking |  | Not Started | 0% | Need test device
Sprint 4 | Nov 18 – Dec 1 | Reports & Alerts | Generate CSV exports, low-stock alert system |  | Not Started | 0% | Planned after CRUD stable
Sprint 5 | Dec 2 – Dec 15 | Final Testing & Presentation | Final demo, cleanup, documentation, presentation |  | Not Started | 0% | Prepare for final presentation

## Gantt
Task | Start Date | End Date | Start Offset (days) | Duration (days)
Sprint 1 — Requirements & Setup | 2025-10-07 | 2025-10-20 | 0 | 14
Sprint 2 — Core CRUD | 2025-10-21 | 2025-11-03 | 14 | 14
Sprint 3 — Barcode & History | 2025-11-04 | 2025-11-17 | 28 | 14
Sprint 4 — Reports & Alerts | 2025-11-18 | 2025-12-01 | 42 | 14
Sprint 5 — Testing & Presentation | 2025-12-02 | 2025-12-15 | 56 | 14